## Template
|  | week 1 | [6 empty] | week 2 | [6 empty] | week 3 | [6 empty] | week 4
Start Date: 08/03/19 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 30 | 1 | 2 | 3 | 4 | 5 | 6
DEVELOPMENT | 0
Finalize Script | 0 | bar: week 1 11 to week 1 12
Attachments | 0
Financing | 0 | bar: week 1 10 to week 4 5
PRE-PRODUCTION | 10
Casting | 2 | bar: week 1 8 to week 1 9
Set Design | 0
Locations | 2 | bar: week 1 10 to week 1 11
Costumes | 2 | bar: week 1 12 to week 1 13
Hair | 2 | bar: week 1 12 to week 1 13
Make-up | 2 | bar: week 1 12 to week 1 13
PRODUCTION | 6
Rehearsals | 3 | bar: week 1 14 to week 2 16
Principal Photography | 3 | bar: week 1 14 to week 2 16
Second Unit | 0
POST-PRODUCTION | 8
Editing | 2 | bar: week 2 19 to week 2 20
VFX | 0
Scoring | 2 | bar: week 2 21 to week 3 22
Sound Editing | 2 | bar: week 2 21 to week 3 22
Color Grading | 2 | bar: week 2 17 to week 2 18
DISTRIBUTION
Distribution Deals
Marketing Push | 6 | bar: week 2 19 to week 3 24
Press Tour
Premieres | 2 | bar: week 3 26 to week 3 27
ANNOTATIONS |  | week 1 8: Film reviews will be sent in by comments on yotube channel as well as screening will be in collage and on youtube and facebook